## Applications
Task | UI | BL | DB | UI Usage
Get applications, filtered for current customer user |  | X | X | GET /api/loan/Applications
Show delete and print operations buttons based on application statuses |  | - | -
Show/Print PDF agreement of finally approved application |  | ? | X
Delete draft application when corresponding operation is selected |  | X | X | Delete /api/loan/Applications/{id}
Get application data on click, show depending on type and status |  | X | X | GET /api/loan/Applications/{id} | GET /api/loan/Applications/{id}/Main
When selecting create application, show new application window with type only /if 00 is selected show aparik data, otherwise non-aparik/ |  | - | -

## Aparik
Task | UI | BL | DB | UI Usage
Validate amount based on type and currency |  | X | X | GET /api/loan/LoanLimits?loanTypeCode={loanTypeCode}currency={currency}
Populate currency based on type |  | X | X | GET /api/loan/Directory/Currencies/{loanType}
Validate all mandatory fields |  | - | -
Validate social card /fixed 10 digits/ |  | - | -
Validate document number, based on document type /if passport should be 2 upper-case alpha chars + fixed 7 digits, if id card should be fixed 9 digits/ |  | - | -
Validate document date /past dates/ |  | - | -
Validate document expiry date /future dates/ |  | - | -
Validate document given by /fixed 3 digits/ |  | - | -
Enable/disable submit based on checkbox selection above it |  | - | -
Show popup with informative message on submit |  | - | -
Populate shop list /parent level only/ |  | TBD | TBD
Populate product receive type |  | X | X | GET /api/loan/Directory/ProductReceivingOptions
Based on product receive type show delivery address, if delivery is selected |  | - | -
Populate product category list |  | X | X | GET /api/loan/Directory/ProductCategories
Populate terms list |  | - | -
Populate loan interest list |  | X | X | GET /api/loan/Applications/{id}/ScroringResults
Validate loan amount, based on interest |  | - | -
Calculate monthly payment amount dynamically, when amount/interest/term fields are modified |  | TBD | X
Validate default repayment day |  | X | X | GET /api/loan/Parameters?loanTypeCode={loanTypeCode}
Validate all mandatory fields |  | - | -
On checking "Same as registration address", fill current address fields values with corresponding registration field values |  | - | -
Enable/disable submit based on checkbox selection above it |  | - | -

## Non aparik
Task | UI | BL | DB | UI Usage
Validate amount based on type and currency |  | X | X | GET /api/loan/LoanLimits?loanTypeCode={loanTypeCode}currency={currency}
Populate currency based on type |  | X | X | GET /api/loan/Directory/Currencies/{loanType}
Validate all mandatory fields |  | - | -
Validate social card /fixed 10 digits/ |  | - | -
Validate document number, based on document type /if passport should be 2 upper-case alpha chars + fixed 7 digits, if id card should be fixed 9 digits/ |  | - | -
Validate document date /past dates/ |  | - | -
Validate document expiry date /future dates/ |  | - | -
Validate document given by /fixed 3 digits/ |  | - | -
Populate business types |  | X | X | GET /api/loan/Directory/Industries
Enable/disable submit based on checkbox selection above it |  | - | -
Show popup with informative message on submit |  | - | -
Populate terms list |  | - | -
Populate loan interest list |  | X | X | GET /api/loan/Applications/{id}/ScroringResults
Populate loan amount, based on interest |  | - | -
Calculate monthly payment amount dynamically, when amount/interest/term fields are modified |  | TBD | X
Validate default repayment day |  | X | X | GET /api/loan/Parameters?loanTypeCode={loanTypeCode}
Validate all mandatory fields |  | - | -
Populate education/work/family lists | X | X | X
Validate card number /fixed 16 digits/ |  | - | -
Validate card expiry date /only future/ |  | - | -
Enable Authorization code fields only after submitting card data |  | ? | ?
Enable/disable accounts/cards data based on loan type
Enable list of accounts/cards if provide new account/card is not selected
Populate list of active accounts
Populate list of active cards
Populate list of card types
Based on card receive type show delivery address, if delivery is selected
Enable/disable submit based on checkbox selection above it

## Registration
Task | UI | BL | DB
Sending authorization code by email after registration

## Design
Design tasks
Default repayment day should be int, not date
Add document/social card scans to aparik
Առաջարկվող Գումար - make amount's caption lower-case
Add Բանկի կողմից քաղվածքների և տեղեկատվության ստացման նախընտրելի եղանակ to aparik
Ցանկանում եմ պատվիրել նոր քարտ կամ բացել նոր հաշիվ should be the first item on page 4
Add print operation button
Design for disabled tabs in applications
Ժամկետ => Արժույթ
Add mobile/email to non-aparik fields